## Estimates Sheet (hidden)
Issue Type | Issue key | Summary | Tasks | UI Effort (Hrs) | Middleware Effort (Hrs) | DB effort (Hrs) | Unit testing Effort(2%) | Review Effort(2%) | Testing/Build Effort(20%) | UAT Effort(2%) | Total Efforts
Bug | SBCP-236 | Region grouping not working correctly in Dashboard | Task 1 | 12 | 6 | 12 | 0.6 | 0.6 | 6 | 0.6 | 37.8
Task | SBCP-252 | Add filter for Region in Dashboard | Task 2
|  | Dashboard Changes | Task 3
|  | Inventory Changes | Task 4
|  | Real Time Refresh Changes | Task 5
Improvement | SBCP-259 | Add Region filter for those Customers who have >1 Region | Task 6
[10 empty] | Total | 37.8

## Resource Loading
Productive hours of Resource | 6 | Week Start |  | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | PD | PD Group wise
Weeks of a Sprint | 3 | Week End |  | 2019-07-19 | 2019-07-26 | 2019-08-02 | 2019-08-09 | 2019-08-16 | 2019-08-23 | 2019-08-30 | 2019-09-06 | 2019-09-13 | 2019-09-20 | 2019-09-27 | 2019-10-04 | 2019-10-11 | 2019-10-18 | 2019-10-25 | 2019-11-01 | 2019-11-08 | 2019-11-15 | 2019-11-22 | 2019-11-29 | 2019-12-06 | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03
No of Days of a Sprint | 15 | Sprints |  | 2019-07-19: Sprint 1; 2019-08-02: Sprint 2; 2019-08-23: Sprint 3; 2019-09-13: Sprint 4; 2019-10-04: Sprint 5; 2019-10-25: Sprint 6; 2019-11-15: Sprint 7; 2019-12-06: Sprint 8; 2019-12-27: Sprint 9; 2020-01-17: Sprint 10; 2020-02-07: Sprint 11; 2020-02-28: Sprint 12; 2020-03-20: Sprint 13
|  | Roles and Resources | # of resources | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32
|  | Product Owner | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | PO
Total Efforts | 3993 | Scrum Master | 1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [6 empty] | 32 | 32 | SM
No of Resources | 3 | Soln Architect | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [6 empty] | 42 | 42 | SA
No of Development resources | 3 | Dev-Mobility-IOS | 1 | [38 empty] | 160 | bar: Sprint 1 Wk1 to Sprint 11 Wk32
No of Hours taken by a resource for a Sprint | 8 | Dev-Mobility-Android | 1 | [38 empty] | 160 | 320 | Dev Mobility | 2720 | bar: Sprint 1 Wk1 to Sprint 11 Wk32
No of Hours taken by 3 resources for a Sprint | 360 | Dev-Python/Django | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 0.6 | [7 empty] | 133 | 133 | Dev API
No of Sprints Required | 11.0917 | QA Lead | 1 | 0.25 | 0.25 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | [6 empty] | 175
|  | QA | 1 | [38 empty] | 150 | 325 | QA | bar: Sprint 2 Wk3 to Sprint 11 Wk32
|  | UX Dev | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 25 | 25 | UX
[14 empty] | PI1 | [8 empty] | PI2 | [8 empty] | PI3
[15 empty] | UAT | UAT | UAT | [6 empty] | UAT | UAT | UAT | [6 empty] | UAT | UAT | UAT
Productive hours of Resource | 6 | Total PDs |  | 21 | 21 | 25.5 | 25.5 | 25.5 | 25.5 | 25.5 | 25.5 | 23.75 | 23.75 | 23.75 | 23.75 | 23.75 | 23.75 | 23.75 | 23.75 | 23.75 | 23.75 | 23.75 | 23.75 | 22.5 | 22.5 | 22.5 | 22.5 | 23 | 18 | 18 | 18 | 18 | 23 | 21 | 18 |  |  |  |  | 727 | PD | 877 | 877 | 193817 | USD
Weeks of a Sprint | 3
No of Days of a Sprint | 15 | Sprints(PH7) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  | Mobility Effort | 70 | 210 | 210 | 210 | 315 | 315 | 315 | 315 | 315 | 315 |  |  |  | 2590 | 2921 |  | Productive Hours |  |  | 6
Total Dev Efforts | 2921 | Python Effort |  | 105 | 105 | 210 | 210 | 210 | 210 | [6 empty] | 1050 | 1072 |  |  |  |  | 7
Effort of for 5 Dev in a Sprint of 3 weeks | 450 | [14 empty] | left | 353 |  |  |  |  | 8
Effort of 2 Dev in a Sprint of 2 weeks | 120
Dev effort left after a Sprint of 2 weeks | 2801 | Sprints(PH8) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
No of 3 Week Sprints required | 6.2244 | Mobility Effort | 80 | 240 | 240 | 240 | 360 | 360 | 360 | 360 | 240 | 240 |  |  |  | 2720 | 2761
|  | Python Effort |  | 120 | 120 | 240 | 240 | 240 | 120 | [6 empty] | 1080 | 1072
No of productive Hours | [15 empty] | left | 33
Total Dev Efforts from Resource Loading of 2 weeks Sprint | 120
Total Dev Efforts from Resource Loading of 3 weeks Sprint | 2310
611
Ideal testing Effort | 876.3
Testing Effort in the Sheet is | 946.5
Total Dev Efforts | 3993
Effort of for 3 Dev in a Sprint of 3 weeks | 315
Effort of 3 Dev in a Sprint of 2 weeks | 210
Dev effort left after a Sprint of 2 weeks | 3783
No of 3 Week Sprints required | 12.0095

## Figure
Sprint Cycles | Sprints / Weeks | Jul'19 |  |  | Aug'19 |  |  |  | Sep'19 |  |  |  | Oct'19 |  |  |  | Nov'19 |  |  |  |  | Dec'19 |  |  |  | Jan'20 |  |  |  |  | Feb'20
|  | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32
1 | Sprint 1 | bar: Jul'19 Wk1 to Jul'19 Wk2
2 | Sprint 2 | bar: Jul'19 Wk3 to Aug'19 Wk5
3 | Sprint 3 | bar: Aug'19 Wk6 to Sep'19 Wk8
4 | Sprint 4 | bar: Sep'19 Wk9 to Sep'19 Wk11
5 | Sprint 5 | bar: Oct'19 Wk12 to Oct'19 Wk14
6 | Sprint 6 | bar: Oct'19 Wk15 to Nov'19 Wk17
7 | Sprint 7 | bar: Nov'19 Wk18 to Nov'19 Wk20
8 | Sprint 8 | bar: Dec'19 Wk21 to Dec'19 Wk23
9 | Sprint 9 | bar: Dec'19 Wk24 to Jan'20 Wk26
10 | Sprint 10 | bar: Jan'20 Wk27 to Jan'20 Wk29
11 | UAT | Oct'19 Wk12: UAT1; Dec'19 Wk24: UAT2

## Sheet3
Sprints /Product Increments | Jul'19 |  |  | Aug'19 |  |  |  | Sep'19 |  |  |  | Oct'19 |  |  |  | Nov'19 |  |  |  |  | Dec'19 |  |  |  | Jan'20 |  |  |  |  | Feb'20
| Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32
Sprint 1 | bar: Jul'19 Wk1 to Jul'19 Wk2
Product Increment 1 | bar: Jul'19 Wk3 to Sep'19 Wk11
UAT 1 | Oct'19 Wk12: UAT 1
Product Increment 2 | bar: Oct'19 Wk12 to Nov'19 Wk20
UAT 2 | Dec'19 Wk21: UAT 2
Product Increment 3 | bar: Dec'19 Wk21 to Jan'20 Wk29
UAT 3 | Feb'20 Wk30: UAT 3
Sprints /Product Increments | Jul'19 Wk1: Wk1; Jul'19 Wk2: Wk2; Jul'19 Wk3: Wk3
Sprint 1 | bar: Jul'19 Wk1 to Jul'19 Wk2
Product Increment 1 | bar: Jul'19 Wk3
UAT 1
Product Increment 2
UAT 2
Product Increment 3
UAT 3

## Mobility+API+ Admin Estimates
Modules | Functional Points | RFP Ref# | Estimated Effort (Duration in Hrs.) |  |  | Product Increment | Categorization(S/M/L) >50-Large,B/w 30 & 50 M,Less than 30 Small
|  |  | iOS | Android | Python / Django API
Landing page | Get user type |  | 32 | 32 |  | PI1 | L | Sprint 1 | Mobility Alone
| Add option to select high school associated with | M3 | 35 | 35 |  | PI1 | L | Sprint 2 |  | Landing Page and Menu
| Get rid of account creation and instead provide a drop list or other selection ability for NC High Schools | M19 | 24 | 32 |  | PI1 | L | Sprint 3 |  | Home Page
| School data API implementation | M3 & M19 |  |  | 40 | PI1 | M | Sprint 4 |  | Visit College NC Pages for IOS
Menu | Configurable menu |  | 35 | 35 |  | PI1 | L | Sprint 5 |  | Visit College NC Page for Android and Main Campus Page for IOS Admin Home Page
| Menu Management API for mobile |  |  |  | 40 | PI1 | M | Sprint 6 |  | Main Campus Page for Android and Content Update Tool for Admin
Home | Major & Degree |  | 16 | 16 |  | PI1 | M | Sprint 7 |  | Disability Access/About Us and Help for Mobile Content Update tool for Admin
| How to college NC |  | 16 | 16 |  | PI1 | M | Sprint 8 |  | Settings/Survey
| Campus Life |  | 16 | 16 |  | PI1 | M | Sprint 9 |  | Common Items across Pages
| Visit College NC |  | 16 | 16 |  | PI1 | M | Sprint 10 |  | Improvement Changes
| 360 video player |  | 32 | 32 |  | PI1 | L
| Configurable Tiles (Add icons on the homepage for additional webpages using full HTML) | M7 | 34 | 34 |  | PI1 | L
| API for Homepage implementation | M7 |  |  | 40 | PI2 | M
Visit College NC | List college | M9 | 32 | 32 |  | PI1 | L
| Search by major | M5 | 24 | 24 |  | PI1 | M
| Filter by GPA, ACT/SAT scores, majors, Cost per year, etc. | M6 | 42 | 42 |  | PI1 | L
| Map view | M9 | 40 | 56 |  | PI1 | L
| Search and filter colleges using URL data driven filtering | M8 | 32 | 32 |  | PI1 | L
| Reverse geo location mapping | M9 | 35 | 35 |  | PI1 | L
| API for List of Colleges | M9 |  |  | 40 | PI1 | M
| API for college search | M5 |  |  | 40 | PI1 | M
| Filter API | M6 |  |  | 32 | PI1 | M
Main campus page | "Admissions" has its own tile and links to college application | M14 | 40 | 40 |  | PI2 | L
| "Financial Aid" and "Degree and Majors" have own separate tiles and link to campus pages for each | M15 | 24 | 24 |  | PI2 | M
| Rename "Contact" section to "Questions?" or "Ask [bot name]" (Email or SMS icon on campus page) | M16 | 30 | 38 |  | PI2 | L
| About section links to campus website | M13 | 32 | 32 |  | PI2 | L
| Move social media icons to each main campus page | M11 | 24 | 24 |  | PI2 | M
| Configurable Tiles (Add full HTML to campus pages) | M12 | 40 | 50 |  | PI2 | L
| API for main campus page and its functionalities |  |  |  | 40 | PI2 | M
Major & Degree/ How to college NC / Campus Life | Career exploration clickable icon that opens a details page | M4 | 38 | 38 |  | PI2 | L
| 360 video |  | 32 | 32 |  | PI2 | L
| API for Major & Degree Page implementation and its functionalities | M4 |  |  | 80 | PI2 | L
Disability access | List college |  | 35 | 35 |  | PI2 | L
| Navigate to YouTube link |  | 20 | 20 |  | PI2 | M
About Us | About GEAR UP NC |  | 40 | 40 |  | PI2 | L
| About GEAR UP NC API |  |  |  | 40 | PI2 | M
Help | App Info/Help Guide | M18 | 64 | 64 |  | PI2 | L
| Help Guide API | M18 |  |  | 40 | PI2 | M
Settings | Terms & Conditions |  | 35 | 35 |  | PI3 | L
| Privacy Policy |  | 30 | 30 |  | PI3 | L
| Push Notification?? |  | 40 | 40 |  | PI3 | L
| Terms & Conditions API |  |  |  | 40 | PI2 | M
Survey | Single selection questions |  | 32 | 32 |  | PI3 | L
| Multiple selection questions |  | 32 | 32 |  | PI3 | L
| Free text questions |  | 32 | 32 |  | PI3 | L
Common | Ask user about opening browser link outside the app vs. inside app with a "Done" option to close | M20 | 24 | 42 |  | PI3 | L
| In-app Browser |  | 24 | 35 |  | PI3 | L
| 360 Video player |  | 80 | 80 |  | PI3 | L
| Follow redesign wireframes | M21 | 64 | 64 |  | PI3 | L
| Project and environment setup |  | 80 | 80 |  | PI3 | L
Improvements | Remove account creation | M2 | 16 | 16 |  | PI3 | M
| Remove "Tour" as menu item | M10 | 16 | 16 |  | PI3 | M
| Improve overall navigation | M17 | 40 | 40 |  | PI3 | L
ADMIN MODULE
Home | Home Page UI & Integration | W7 |  |  | 40 | PI2 | M | 30 |  | 600 | 530 | 70 | 8.2353
| Tool for edit Homepage | AT5 |  |  | 40 | PI2 | M | 40 |  | MOBILE PD | 117.8824
Login / Profile | Login Page for web app |  |  |  | 40 | PI2 | M | 20
| Profile section for administrator |  |  |  | 40 | PI2 | M | 30
| Change password for administrator |  |  |  | 40 | PI2 | M | 10
Menu | Page for edit menu items | AT2 |  |  | 40 | PI2 | M | 40
Content Update Tool | Edit School Pages | AT3 |  |  | 80 | PI2 | L | 80
| Edit Topic Pages | AT4 |  |  | 80 | PI2 | L | 80
| Youtube integration tool | AT6 |  |  | 40 | PI2 | M | Hrs per Day | 8.5
| Edit content on all site | AT1 |  |  | 160 | PI2 | L | Total Weeks | 30
[8 empty] | QA %` | 50%
[8 empty] | SM/PO | 10%
[8 empty] | Mobile Hrs | Mobile PD | API PD
Total Development Effort (in Hrs.) |  |  | 1425 | 1496 | 712 | 1002 |  | 2921 | 343.6471 | 117.8824 | Dev PD
Testing/Build Effort (in Hrs.) |  |  | 712.5 | 748 | 356 |  |  | 1460.5 | 171.8235 | 41.8824 | QA PD
|  |  | 2137.5 | 2244 | 1068
Total (in Hrs.) |  |  | Hrs | 5449.5 |  |  |  |  | 2.291 | 0.78588 | Dev resources for x weeks
Total PD (Dev+QA) |  | Total PD | Efforts in PD | 641.1176 |  |  |  |  | 1.1455 | 0.27922 | QA resource for x weeks
|  | PO | Efforts in PD | 64.1118
|  | SM | Efforts in PD | 64.1118 |  |  |  |  | 1.1455 | Android Dev for x weeks
|  | UX | Efforts in PD | 75 | 1 UX throughout? |  |  |  | 1.1455 | iOS Dev for x weeks
|  | Solun Architect | Efforts in PD | 75 | 1 SA throughout
|  | Total | Efforts in PD | 919.3412
|  |  | USD | 203174.4
|  |  | USD | 2902.4914 | Per feature and/or screen
|  |  | PD | 13.1334 | Per feature and/or screen

## Sheet1
|  | Estimated Effort (Duration in Hrs.) |  |  | Hrs per Day | 8.5
|  | iOS | Android | Python / Django API | Total Weeks | 30
Total Development Effort (in Hrs.) |  | 1425 | 1496 | 1002 | QA %` | 50%
Testing/Build Effort (in Hrs.) |  | 712.5 | 748 | 501 | SM/PO | 10%
|  | 2137.5 | 2244 | 1503
Total (in Hrs.) |  | Hrs | 5884.5
Total PD (Dev+QA) | Total PD | Efforts in PD | 692.2941 |  | Mobile Hrs | Mobile PD | API PD
| PO | Efforts in PD | 69.2294 |  | 2921 | 343.6471 | 117.8824 | Dev PD
| SM | Efforts in PD | 69.2294 |  | 1140.5 | 134.1765 | 58.9412 | QA PD
| UX | Efforts in PD | 75 | 1 UX throughout?
| Solun Architect | Efforts in PD | 75 | 1 SA throughout
| Total | Efforts in PD | 980.7529
|  | USD | 216746.4
|  | USD | 3096.3771 | Per feature and/or screen
|  | PD | 14.0108 | Per feature and/or screen
518532
Note on G3: Kiran Rachel George: revised after discussions with Bimal and Nitish

## Mobility Estimates (hidden)
Modules | Functional Points | RFP Ref# | Estimated Effort (Duration in Hrs.)
|  |  | iOS | Android
Landing page | Get user type |  | 32 | 32
| Add option to select high school associated with | M3 | 35 | 35
| Get rid of account creation and instead provide a drop list or other selection ability for NC High Schools | M19 | 24 | 32
Menu | Configurable menu |  | 35 | 35
Home | Major & Degree |  | 16 | 16
| How to college NC |  | 16 | 16
| Campus Life |  | 16 | 16
| Visit College NC |  | 16 | 16
| 360 video player |  | 32 | 32
| Configurable Tiles (Add icons on the homepage for additional webpages using full HTML) | M7 | 34 | 34
Visit College NC | List college | M9 | 32 | 32
| Search by major | M5 | 24 | 24
| Filter by GPA, ACT/SAT scores, majors, Cost per year, etc. | M6 | 42 | 42
| Map view | M9 | 40 | 56
| Search and filter colleges using URL data driven filtering | M8 | 32 | 32
| Reverse geo location mapping | M9 | 35 | 35
Main campus page | "Admissions" has its own tile and links to college application | M14 | 40 | 40
| "Financial Aid" and "Degree and Majors" have own separate tiles and link to campus pages for each | M15 | 24 | 24
| Rename "Contact" section to "Questions?" or "Ask [bot name]" (Email or SMS icon on campus page) | M16 | 30 | 38
| About section links to campus website | M13 | 32 | 32
| Move social media icons to each main campus page | M11 | 24 | 24
| Configurable Tiles (Add full HTML to campus pages) | M12 | 40 | 50
Major & Degree/ How to college NC / Campus Life | Career exploration clickable icon that opens a details page | M4 | 38 | 38
| 360 video |  | 32 | 32
Disability access | List college |  | 35 | 35
| Navigate to YouTube link |  | 20 | 20
About Us | About GEAR UP NC |  | 40 | 40
Help | App Info/Help Guide | M18 | 64 | 64
Settings | Terms & Conditions |  | 35 | 35
| Privacy Policy |  | 30 | 30
| Push Notification?? |  | 40 | 40
Survey | Single selection questions |  | 32 | 32
| Multiple selection questions |  | 32 | 32
| Free text questions |  | 32 | 32
Common | Ask user about opening browser link outside the app vs. inside app with a "Done" option to close | M20 | 24 | 42
| In-app Browser |  | 24 | 35
| 360 Video player |  | 80 | 80
| Follow redesign wireframes | M21 | 64 | 64
| Project and environment setup |  | 80 | 80
Improvements | Remove account creation | M2 | 16 | 16
| Remove "Tour" as menu item | M10 | 16 | 16
| Improve overall navigation | M17 | 40 | 40
Total Development Effort (in Hrs.) |  |  | 1425 | 1496 | 2921
Testing/Build Effort (in Hrs.) |  |  | 285 | 299.2
|  |  | 1710 | 1795.2
Total (in Hrs.) |  |  | 3505.2